## Issues Log
14 | User Story (Task) | Task Description | Task Holder | Esitmation (In Days) | Priority | Task Status | Comments
3 | Code to read xml file recursively. | Code we need to create so that we can read the xml file recursively. This mock code should be able to read any valid xml file. | dev 2 | 1 | 2
2 | Code to check if xml file is valid. | Need to develop code to check if the provided xml file is valid XML file as per industry standards. | dev 1 | 0.5 | 1
6 | Logger | Need a utility to log errors. This can be taken from any open source, or can be developed. If client is already using it we need to conform and take the same plugin. | not assigned | 2 | 3 |  | Discussion with client and taking client's opinion
4 | A standard wrapper code to hold the xml data. | Need to finalize the architecture to hold all the data which is been read from xml files. | not assigned | 2 | 2
5 | Utility to query the data kept in the memory. | The code need to be developed for searching the required keys, attributes, xml elements, element's xml data, inner text of xml element. Client is using 4.5 version we contains linq and lambda as well, so we should use the same for searching utility. | not assigned | 2 | 2 |  | Client interest need here what will be the best possible search he is looking for.
1 | Project set up for mock demo | Creation of project for demo and the same will be taken further to establish the plugin. | dev 1 | 1 | 1
7 | QA verification for task 2 | Verify the task 2 is running fine. | dev 2 | 0.25 | 1
8 | QA verification for task 3 | Verify whether task 3 reading and displaying the correct data. | dev 1 | 0.25 | 1
9 | QA Build Release | After verfication releasing build | dev 1 & 2 | 0.5 | 1
10 | QC Testing for task 2 & 3 and raising bug(s) if any. | Testing | QC 1 | 1 | 1
11 | QA Bug(s) fixing if any | Bug fixing | dev 1 & 2 | 0.5 | 1
12 | QA Build Release After Bug fixing. | Re-testing | dev 1 & 2 | 0.25 | 1
13 | QC Re-Testing for task 2 & 3 along with bugs and making demo ready. | Version 1.0.0.1 release. | QC 1 | 0.25 | 1

## Iteration 1
TaskId | Task | Esitmate | Status |  | Days
1 | Project set up for mock demo | 1 | 0 | Start Date | 2015-03-02
2 | Code to check if xml file is valid. | 0.5 | 0 | No. of working days | 6
3 | Code to read xml file recursively. | 1 | 0 | No. of Developer & QC | 3
7 | QA verification for task 2 | 0.25 | 0 | No. of days for Development & QC | 18
8 | QA verification for task 3 | 0.25 | 0 | Efficiency Factor | 0.69
9 | QA Build Release | 0.5 | 0 | Actual Development & QC Days | 12.42
10 | QC Testing for task 2 & 3 and raising bug(s) if any. | 1 | 0 | End Date | 2015-03-08
11 | QA Bug(s) fixing if any | 0.5 | 0 | Backlog as per effiency | -2.07
12 | QA Build Release After Bug fixing. | 0.5 | 0 | Days used for backlog | 3
13 | QC Re-Testing for task 2 & 3 along with bugs and making demo ready. | 0.5 | 0
| Total Days to release Version 1.0.0.1 | 6
| Calculated Available or Assign Time | 6.42

## Iteration 1 BurnDown
Work Day | Work Days | Ideal Remaining effort | Actual Remaining Task (For Chart) | Developer 1 Task Completed | Developer 2 Task Completed | QA 1 Testing and Fixing | QA 2 Testing and Fixing | QC Testing & Finding Bugs | QA Bug Fixing | QC Testing & Releasing | Total Task Completed | Actual Remaining Task | Man Days Used | Calculated Efficency Factor | BackLogs In Days | Esitimate Days | Backlogs as per efficency | Actual Working Days
| 0 | 12.4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 3 | 6 | -2.07 | 12.42
2015-03-02 | 1 | 10.4 | 4.6 | 0.5 | 0.9 | 0 | 0 | 0 | 0 | 0 | 1.4 | 4.6 | 3 | 0.47 | 3 | 6 | -2.07 | 12.42
2015-03-03 | 2 | 8.3 | 3.5 | 0.75 | 0.35 | 0 | 0 | 0 | 0 | 0 | 2.5 | 3.5 | 6 | 0.42 | 3 | 6 | -2.07 | 12.42
2015-03-04 | 3 | 6.2 | 2.6 | 0 | 0 | 0.5 | 0.4 | 0 | 0 | 0 | 3.4 | 2.6 | 9 | 0.38 | 3 | 6 | -2.07 | 12.42
2015-03-05 | 4 | 4.1 | 1.2 | 0 | 0 | 0 | 0.1 | 0.9 | 0.4 | 0 | 4.8 | 1.2 | 12 | 0.4 | 3 | 6 | -2.07 | 12.42
2015-03-06 | 5 | 2.1 | 0.45 | 0 | 0 | 0 | 0 | 0.1 | 0.6 | 0.05 | 5.55 | 0.45 | 15 | 0.37 | 3 | 6 | -2.07 | 12.42
2015-03-07 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 6 | 0 | 18 | 0.33 | 3 | 6 | -2.07 | 12.42