## Issues Log
30 | User Story (Task) | Task Description | Task Holder | Esitmation (In Days) | Priority | Task Status | Comments
3 | Code to read xml file recursively. | Code we need to create so that we can read the xml file recursively. This mock code should be able to read any valid xml file. | dev 2 | 1 | 2 | DONE
2 | Code to check if xml file is valid. | Need to develop code to check if the provided xml file is valid XML file as per industry standards. | dev 1 | 0.5 | 1 | REFER: 27 | If file is invalid configuration should log the erroe in log file but application should not be stopped. Please refer to new taskid number: 27
6 | Logger | Need a utility to log errors. This can be taken from any open source, or can be developed. If client is already using it we need to conform and take the same plugin. | not assigned | 2 | 3 | REFER: 14 | Discussion with client and taking client's opinion. Client asked to create a new utility for the same. Pleas refer new taskid number: 14
4 | A standard wrapper code to hold the xml data. | Need to finalize the architecture to hold all the data which is been read from xml files. | not assigned | 2 | 2 | REFER: 28 | New Class Library for all existing codes. Please refer to new taskid number: 28
5 | Utility to query the data kept in the memory. | The code need to be developed for searching the required keys, attributes, xml elements, element's xml data, inner text of xml element. Client is using 4.5 version we contains linq and lambda as well, so we should use the same for searching utility. | not assigned | 2 | 2 | REFER: 20 | Client interest need here what will be the best possible search he is looking for. Client is confortable with normal search using LINQ or Lambda equation. Please refer to new taskid number: 20
1 | Project set up for mock demo | Creation of project for demo and the same will be taken further to establish the plugin. | dev 1 | 1 | 1 | DONE
7 | QA verification for task 2 | Verify the task 2 is running fine. | dev 2 | 0.25 | 1 | DONE
8 | QA verification for task 3 | Verify whether task 3 reading and displaying the correct data. | dev 1 | 0.25 | 1 | DONE
9 | QA Build Release | After verfication releasing build | dev 1 & 2 | 0.5 | 1 | DONE
10 | QC Testing for task 2 & 3 and raising bug(s) if any. | Testing | QC 1 | 1 | 1 | DONE
11 | QA Bug(s) fixing if any | Bug fixing | dev 1 & 2 | 0.5 | 1 | DONE
12 | QA Build Release After Bug fixing. | Re-testing | dev 1 & 2 | 0.25 | 1 | DONE
13 | QC Re-Testing for task 2 & 3 along with bugs and making demo ready. | Version 1.0.0.1 release. | QC 1 | 0.25 | 1 | DONE
14 | Create new configuration for log utility | The configuration of log utility. Namespace should ReadXml.Logger | dev 1 | 1 | 1
15 | Log configuration elements | Logger should have section name and elements should be 1. Folder: Place where log files will be stored. Required 2. File: The name of the log file default should be "logs.text". Required 3. FileSize: The size of log files should be by default 1024 MB. Required 4. RollDaily: New file should be made daily basis, by default the property should be true. Required | dev 1 | 1 | 1
16 | Log Logger | Functionality to log exception into log file. | dev 1 | 0.5 | 1
17 | QA Testing for logger | Verfication of logger | dev 2 | 0.5 | 3
18 | Refactoring business logic of reading xml file into one wrapper. | The mock code should be refactor and generically re-written. There can be more then one xml (configuration) file. | dev 2 | 1 | 2
19 | Search by xml element name returning value of xml element | Search utility | dev 2 | 0.125 | 2
20 | Search by xml element name returning innerxml | Search utility | dev 2 | 0.125 | 2
21 | Search by xml element name returning innertext | Search utility | dev 2 | 0.125 | 2
22 | Search by xml element name returning xml node without child(s) | Search utility | dev 2 | 0.125 | 2
23 | Search by xml element name returning xml node with child(s) | Search utility | dev 2 | 0.125 | 2
24 | Search by xml attribute name returning value of attribute | Search utility | dev 2 | 0.125 | 2
25 | Search by xml attribute name returning xml element of which it belongs | Search utility | dev 2 | 0.125 | 2
26 | While reading configuration file is there are errors they should be stored in memory and all errors should be retrival. | Search utility | dev 2 | 0.125
27 | While reading or searching if there is any error the same should be logged. If searching any element or attribute the return should be null | Logging the errors while reading configuration files and searching | dev 2 | 0.125
28 | Storage utility wrapper | Creating a static storage where configuration data would be kept into memory | dev 1 | 1
29 | QA verfication for search | Veficiation of code | dev 1 | 0.75

## Iteration 2
TaskId | Task | Esitmate | Status |  | Days
14 | Create new configuration for log utility | 1 | 0 | Start Date | 2015-03-09
15 | Log configuration elements | 1 | 0 | No. of working days | 7
16 | Log Logger | 0.5 | 0 | No. of Developer & QC | 2
17 | QA Testing for logger | 0.5 | 0 | No. of days for Development & QC | 14
18 | Refactoring business logic of reading xml file into one wrapper. | 1 | 0 | Efficiency Factor | 0.7
19 | Search by xml element name returning value of xml element | 0.125 | 0 | Actual Development & QC Days | 9.8
20 | Search by xml element name returning innerxml | 0.125 | 0 | End Date | 2015-03-16
21 | Search by xml element name returning innertext | 0.125 | 0 | Backlog as per effiency | -1.4
22 | Search by xml element name returning xml node without child(s) | 0.125 | 0 | Days used for backlog | 2
23 | Search by xml element name returning xml node with child(s) | 0.125 | 0
24 | Search by xml attribute name returning value of attribute | 0.125 | 0
25 | Search by xml attribute name returning xml element of which it belongs | 0.125 | 0
26 | While reading configuration file is there are errors they should be stored in memory and all errors should be retrival. | 0.125 | 0
27 | While reading or searching if there is any error the same should be logged. If searching any element or attribute the return should be null | 0.125 | 0
28 | Storage utility wrapper | 1 | 0
29 | QA verfication for search | 0.75 | 0
| Total Days to release Version 1.0.0.2 | 6.875
| Calculated Available or Assign Time | 2.925

## Iteration 2 BurnDown
Work Day | Work Days | Ideal Remaining effort | Actual Remaining Task (For Chart) | Developer 1 Task Completed | Developer 2 Task Completed | QA 1 Testing and Fixing | QA 2 Testing and Fixing | QC Testing & Finding Bugs | QA Bug Fixing | QC Testing & Releasing | Total Task Completed | Actual Remaining Task | Man Days Used | Calculated Efficency Factor | BackLogs In Days | Esitimate Days | Backlogs as per efficency | Actual Working Days
| 0 | 9.8 | 6.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875 | 0 | 0 | 2 | 6.875 | -1.4 | 9.8
2015-03-09 | 1 | 8.4 | 5.075 | 0.85 | 0.95 | 0 | 0 | 0 | 0 | 0 | 1.8 | 5.075 | 2 | 0.9 | 2 | 6.875 | -1.4 | 9.8
2015-03-10 | 2 | 7 | 3.425 | 0.9 | 0.75 | 0 | 0 | 0 | 0 | 0 | 3.45 | 3.425 | 4 | 0.86 | 2 | 6.875 | -1.4 | 9.8
2015-03-11 | 3 | 5.6 | 2.852 | 0.45 | 0.123 | 0 | 0 | 0 | 0 | 0 | 4.023 | 2.852 | 6 | 0.67 | 2 | 6.875 | -1.4 | 9.8
2015-03-12 | 4 | 4.2 | 1.75 | 0.3 | 0.302 | 0 | 0.5 | 0 | 0 | 0 | 5.125 | 1.75 | 8 | 0.64 | 2 | 6.875 | -1.4 | 9.8
2015-03-13 | 5 | 2.8 | 1.05 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 5.825 | 1.05 | 10 | 0.58 | 2 | 6.875 | -1.4 | 9.8
2015-03-14 | 6 | 1.4 | 0.05 | 0.3 | 0 | 0.7 | 0 | 0 | 0 | 0 | 6.825 | 0.05 | 12 | 0.57 | 2 | 6.875 | -1.4 | 9.8
2015-03-16 | 7 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 6.875 | 0 | 14 | 0.49 | 2 | 6.875 | -1.4 | 9.8
Formulas:
Work Day = [Work Day, row above]+1